## Sheet1
Project Name | On point Analytic Inc. Expansion Plan
ProjectManager | Mr. Carlos
Project Deliverable | Database and Data Warehousing
Start Date | 2020-03-05
End Date | 2020-11-01 |  | [Months are subdivided into weeks]
Overall Progress
Task | Responsibility | Duration(Days) | Start | End | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Concept Initiation | Mr. Carlos | 7 | 2020-05-03 | 2020-05-10 | Complete
Budget Allocation | On point Analytic | 7 | 2020-05-10 | 2020-05-17 | Complete
Feasibility Study | Mr. Carlos | 7 | 2020-05-17 | 2020-05-24 | Complete
Technical Feasibility | Mr. Carlos | 1 | 2020-05-17 | 2020-05-18 | Complete
Operational Feasibility | Mr. Carlos | 1 | 2020-05-18 | 2020-05-19 | Complete
Economic Feasibility | Mr. Carlos | 2 | 2020-05-19 | 2020-05-21 | Complete
Operational Feasibility | On point Analytic | 1 | 2020-05-21 | 2020-05-22 | Complete
Schedule Feasibility | Mr. Carlos Castano | 2 | 2020-05-22 | 2020-05-24 | Complete
Project planning | Mr. Jefferson | 7 | 2020-05-24 | 2020-05-31 | Incomplete
Software design | Mr. John Carrey | 44 | 2020-06-07 | 2020-07-21 | Incomplete
Requirment specification
Forming Team
Budget Allocation
Design | Procurement Office | 14 | 2020-07-05 | 2020-07-19 | Incomplete
Material Procurement | Outsourced | 14 | 2020-07-19 | 2020-08-02 | Incomplete
Network Installation | Outsourced | 14 | 2020-08-02 | 2020-08-16 | Incomplete
Hardware Installation | Mr. John Carrey | 77 | 2020-06-07 | 2020-08-23 | Incomplete
Software developmment | Mr. Jefferson | 28 | 2020-08-16 | 2020-09-13 | Incomplete
Requirements and Architecture |  | 1 | 2020-08-16 | 2020-08-17 | Incomplete
System detailed design |  | 15 | 2020-08-17 | 2020-09-01 | Incomplete
System Integration |  | 7 | 2020-09-01 | 2020-09-08 | Incomplete
System Verification |  | 1 | 2020-09-08 | 2020-09-09 | Incomplete
Operation and maintanance |  | 4 | 2020-09-09 | 2020-09-13 | Incomplete
System analysis 1 | Mr. Carlos | 21 | 2020-09-06 | 2020-09-27 | Incomplete
System Testing | Mr. Carlos | 7 | 2020-09-20 | 2020-09-27 | Incomplete
Initial Implementation | Outsourced | 49 | 2020-08-16 | 2020-10-04 | Incomplete
Documentation | Mr. John Carrey | 14 | 2020-10-04 | 2020-10-18 | Incomplete
Full implementation | Mr. Jefferson | 7 | 2020-10-18 | 2020-10-25 | Incomplete
Performance control | Mr. Carlos | 7 | 2020-10-25 | 2020-11-01 | Incomplete
Project close